## Report
WEEKLY REPORT
WEEK: 7
No. | Task | From | To | Assign to | Estimate Time | Actual Time
1 | Team Meeting | 14/11/2016 | 14/11/2016 | HaiTran |  | 3
2 | Training Technical | 15/11/2016 | 15/11/2016 |  | 2 | 2
3 | Update Measurement Plan | 16/11/2016 | 17/11/2016 |  | 5 | 4
4 | Presenstation | 17/11/2016 | 17/11/2016 |  | 2 | 3
5 | Modify Requirement Plan | 18/11/2016 | 19/11/2016 |  | 4 | 5
6 | Update document structure | 18/11/2016 | 19/11/2016 |  | 2 | 2
7 | Update schedule | 18/11/2016 | 19/11/2016 |  | 3 | 2
8 | Team Meeting | 14/11/2016 | 14/11/2016 | HienNguyen |  | 3
9 | Training Technical | 15/11/2016 | 15/11/2016 |  | 2 | 2
10 | Update Risk Management Plan | 16/11/2016 | 17/11/2016 |  | 6 | 8
11 | Presenstation | 17/11/2016 | 17/11/2016 |  | 2 | 3
12 | Modify Architecture and design plan | 18/11/2016 | 19/11/2016 |  | 3 | 6
13 | Team Meeting | 14/11/2016 | 14/11/2016 | KhoiNguyen |  | 3
14 | Training Technical | 15/11/2016 | 15/11/2016 |  | 2 | 2
15 | Update Risk Management Plan | 16/11/2016 | 17/11/2016 |  | 5 | 6
16 | Presenstation | 17/11/2016 | 17/11/2016 |  | 2 | 3
17 | Modify Configuration Plan | 18/11/2016 | 19/11/2016 |  | 5 | 7
18 | Update document structure | 18/11/2016 | 19/11/2016 |  | 3 | 3
19 | Update configuration process | 18/11/2016 | 19/11/2016 |  | 3 | 1
20 | Team Meeting | 14/11/2016 | 14/11/2016 | MinhDoan |  | 3
21 | Training Technical | 15/11/2016 | 15/11/2016 |  | 2 | 2
22 | Update Change Management Plan | 16/11/2016 | 17/11/2016 |  | 8 | 7
23 | Presenstation | 17/11/2016 | 17/11/2016 |  | 2 | 3
24 | Modify Risk Management plan | 18/11/2016 | 19/11/2016 |  | 4 | 6
25 | Team Meeting | 14/11/2016 | 14/11/2016 | TaiNguyen |  | 3
26 | Training Technical | 15/11/2016 | 15/11/2016 |  | 2 | 2
27 | Update Measurement Plan | 16/11/2016 | 17/11/2016 |  | 6 | 4
28 | Presenstation | 17/11/2016 | 17/11/2016 |  | 2 | 3
29 | Modify Change Management plan | 18/11/2016 | 19/11/2016 |  | 3 | 5
30 | Update development process | 18/11/2016 | 19/11/2016 |  | 3 | 2
31 | Update measurement and control process | 18/11/2016 | 19/11/2016 |  | 2 | 2
32 | Team Meeting | 14/11/2016 | 14/11/2016 | XuanThaiHien |  | 3
33 | Training Technical | 15/11/2016 | 15/11/2016 |  | 2 | 2
34 | Update Change Management Plan | 16/11/2016 | 17/11/2016 |  | 7 | 5
35 | Presenstation | 17/11/2016 | 17/11/2016 |  | 2 | 3
36 | Modify Test plan | 18/11/2016 | 19/11/2016 |  | 5 | 3
37 | Update change management process | 18/11/2016 | 19/11/2016 |  | 2 | 1
[5 empty] | ESTIMATE | ACTUAL
|  | Total |  | HaiTran | 18 | 21
|  |  |  | HienNguyen | 13 | 22
|  |  |  | KhoiNguyen | 20 | 25
|  |  |  | MinhDoan | 16 | 21
|  |  |  | TaiNguyen | 18 | 21
|  |  |  | XuanThaiHien | 18 | 17

## HaiTran
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## HienNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## KhoiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## TaiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## MinhDoan
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## XuanThaiHien
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time