## Report
WEEKLY REPORT
WEEK: 8
No. | Task | From | To | Assign to | Estimate Time | Actual Time
1 | Team Meeting | 21/11/2016 | 21/11/2016 | HaiTran | 2 | 3
2 | Mentor Meeting | 21/11/2016 | 21/11/2016 |  | 3 | 3
3 | Training Technical | 22/11/2016 | 22/11/2016 |  | 2 | 2
4 | Customer Meeting | 22/11/2016 | 22/11/2016 |  | 3 | 2
5 | Analyze Requirement | 22/11/2016 | 23/11/2016 |  | 6 | 6
6 | Develop Business workflow "Manage Accounts" function | 22/11/2016 | 23/11/2016 |  | 4 | 5
7 | Develop Business workflow "Manage News" function | 24/11/2016 | 25/11/2016 |  | 6 | 4
8 | Team Meeting | 21/11/2016 | 21/11/2016 | HienNguyen | 2 | 3
9 | Mentor Meeting | 21/11/2016 | 21/11/2016 |  | 3 | 3
10 | Training Technical | 22/11/2016 | 22/11/2016 |  | 2 | 2
11 | Customer Meeting | 22/11/2016 | 22/11/2016 |  | 3 | 2
12 | Analyze Requirement | 22/11/2016 | 23/11/2016 |  | 8 | 7
13 | Develop Business workflow "Manage Homepage" function | 24/11/2016 | 26/11/2016 |  | 6 | 8
14 | Team Meeting | 21/11/2016 | 21/11/2016 | KhoiNguyen | 2 | 3
15 | Mentor Meeting | 21/11/2016 | 21/11/2016 |  | 3 | 3
16 | Training Technical | 22/11/2016 | 22/11/2016 |  | 2 | 2
17 | Customer Meeting | 22/11/2016 | 22/11/2016 |  | 3 | 2
18 | Analyze Requirement | 22/11/2016 | 23/11/2016 |  | 8 | 6
19 | Develop Business workflow "Manage FAQ" function | 24/11/2016 | 25/11/2016 |  | 5 | 6
20 | Develop Business workflow "Manage Languages" function | 24/11/2016 | 26/11/2016 |  | 1 | 1
21 | Team Meeting | 21/11/2016 | 21/11/2016 | MinhDoan | 2 | 3
22 | Mentor Meeting | 21/11/2016 | 21/11/2016 |  | 3 | 3
23 | Training Technical | 22/11/2016 | 22/11/2016 |  | 2 | 2
24 | Customer Meeting | 22/11/2016 | 22/11/2016 |  | 3 | 2
25 | Analyze Requirement | 22/11/2016 | 23/11/2016 |  | 9 | 7
26 | Develop Business workflow "Manage Categories " function | 24/11/2016 | 26/11/2016 |  | 6 | 5
27 | Team Meeting | 21/11/2016 | 21/11/2016 | TaiNguyen | 2 | 3
28 | Mentor Meeting | 21/11/2016 | 21/11/2016 |  | 3 | 3
29 | Training Technical | 22/11/2016 | 22/11/2016 |  | 2 | 2
30 | Customer Meeting | 22/11/2016 | 22/11/2016 |  | 3 | 2
31 | Analyze Requirement | 22/11/2016 | 23/11/2016 |  | 7 | 7
32 | Develop Business workflow "Manage Banners" function | 24/11/2016 | 25/11/2016 |  | 3 | 2
33 | Develop Business workflow "Manage Pop-ups" function | 24/11/2016 | 25/11/2016 |  | 3 | 1
34 | Team Meeting | 21/11/2016 | 21/11/2016 | XuanThaiHien | 2 | 3
35 | Mentor Meeting | 21/11/2016 | 21/11/2016 |  | 3 | 3
36 | Training Technical | 22/11/2016 | 22/11/2016 |  | 2 | 2
37 | Customer Meeting | 22/11/2016 | 22/11/2016 |  | 3 | 2
38 | Analyze Requirement | 22/11/2016 | 23/11/2016 |  | 5 | 7
39 | Develop Business workflow "Manage Examination " function | 24/11/2016 | 26/11/2016 |  | 5 | 3
[5 empty] | ESTIMATE | ACTUAL
|  | Total |  | HaiTran | 26 | 25
|  |  |  | HienNguyen | 24 | 25
|  |  |  | KhoiNguyen | 16 | 23
|  |  |  | MinhDoan | 25 | 22
|  |  |  | TaiNguyen | 23 | 20
|  |  |  | XuanThaiHien | 20 | 20

## HaiTran
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## HienNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## KhoiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## TaiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## MinhDoan
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## XuanThaiHien
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time