## Sheet1
EFFORT LOG
WEEK: 9
No. | Task | From | To | Estimate Time | Actual Time
1 | Team Meeting | 28/11/2016 | 28/11/2016 |  | 3
2 | Review Business Workflow "Manage Account"function | 28/11/2016 | 28/11/2016 | 3 | 5
3 | Review Business Workflow "Manage Homepage" function | 29/11/2016 | 29/11/2016 | 2 | 5
4 | Review Business Workflow "Manage Languages" function | 29/11/2016 | 29/11/2016 | 1 | 1
5 | Training Technical | 29/11/2016 | 29/11/2016 | 2 | 2
6 | Update Business workflow "Manage Accounts" function | 30/11/2016 | 2016-01-12 | 5 | 4
7 | Update Business workflow "Manage News" function | 30/11/2016 | 2016-01-12 | 5 | 7
8 | Define Proposed System | 2016-01-12 | 2016-01-12 | 4 | 2
9 | Define analysis summarizing future system | 2016-02-12 | 2016-03-12 | 3 | 5