## Sheet1
EFFORT LOG
WEEK: 9
No. | Task | From | To | Estimate Time | Actual Time
1 | Team Meeting | 28/11/2016 | 28/11/2016 |  | 3
2 | Review Business Workflow "Manage Banners" function | 28/11/2016 | 28/11/2016 | 2 | 3
3 | Review Business Workflow "Manage Pop-ups" function | 29/11/2016 | 29/11/2016 | 2 | 2
4 | Review Business Workflow "Manage Examination " function | 29/11/2016 | 29/11/2016 | 2 | 3
5 | Training Technical | 29/11/2016 | 29/11/2016 | 2 | 2
6 | Update Business workflow "Manage Examination " function | 30/11/2016 | 2016-01-12 | 2 | 3
7 | Define Business Context | 2016-01-12 | 2016-01-12 | 2 | 3