## Report
WEEKLY REPORT
WEEK: 9
No. | Task | From | To | Assign to | Estimate Time | Actual Time
1 | Team Meeting | 28/11/2016 | 28/11/2016 | HaiTran |  | 3
2 | Review Business Workflow "Manage Account"function | 28/11/2016 | 28/11/2016 |  | 3 | 5
3 | Review Business Workflow "Manage Homepage" function | 29/11/2016 | 29/11/2016 |  | 2 | 5
4 | Review Business Workflow "Manage Languages" function | 29/11/2016 | 29/11/2016 |  | 1 | 1
5 | Training Technical | 29/11/2016 | 29/11/2016 |  | 2 | 2
6 | Update Business workflow "Manage Accounts" function | 30/11/2016 | 2016-01-12 |  | 5 | 4
7 | Update Business workflow "Manage News" function | 30/11/2016 | 2016-01-12 |  | 5 | 7
8 | Define Proposed System | 2016-01-12 | 2016-01-12 |  | 4 | 2
9 | Define analysis summarizing future system | 2016-02-12 | 2016-03-12 |  | 3 | 5
10 | Team Meeting | 28/11/2016 | 28/11/2016 | HienNguyen |  | 3
11 | Review Business Workflow "Manage Account"function | 28/11/2016 | 28/11/2016 |  | 4 | 5
12 | Review Business Workflow "Manage FAQ" function | 29/11/2016 | 29/11/2016 |  | 3 | 2
13 | Review Business Workflow "Manage Categories " function | 29/11/2016 | 29/11/2016 |  | 4 | 4
14 | Training Technical | 29/11/2016 | 29/11/2016 |  | 2 | 2
15 | Update Business workflow "Manage Homepage" function | 30/11/2016 | 2016-01-12 |  | 3 | 5
16 | Define Vision of the soulution | 2016-01-12 | 2016-01-12 |  | 5 | 5
17 | Define Summary of impacts | 2016-02-12 | 2016-03-12 |  | 2 | 4
18 | Team Meeting | 28/11/2016 | 28/11/2016 | KhoiNguyen |  | 3
19 | Review Business Workflow "Manage News" function | 28/11/2016 | 28/11/2016 |  | 3 | 4
20 | Review Business Workflow "Manage FAQ" function | 29/11/2016 | 29/11/2016 |  | 4 | 2
21 | Review Business Workflow "Manage Languages" function | 29/11/2016 | 29/11/2016 |  | 1 | 1
22 | Training Technical | 29/11/2016 | 29/11/2016 |  | 2 | 2
23 | Update Business workflow "Manage FAQ" function | 30/11/2016 | 2016-01-12 |  | 4 | 5
24 | Define Scope and Limitations | 2016-01-12 | 2016-01-12 |  | 3 | 6
25 | Define Justification of Changes | 2016-02-12 | 2016-03-12 |  | 2 | 5
26 | Team Meeting | 28/11/2016 | 28/11/2016 | MinhDoan |  | 3
27 | Review Business Workflow "Manage News" function | 28/11/2016 | 28/11/2016 |  | 4 | 4
28 | Review Business Workflow "Manage Pop-ups" function | 29/11/2016 | 29/11/2016 |  | 3 | 2
29 | Review Business Workflow "Manage Examination " function | 29/11/2016 | 29/11/2016 |  | 3 | 3
30 | Training Technical | 29/11/2016 | 29/11/2016 |  | 2 | 2
31 | Update Business workflow "Manage Categories " function | 30/11/2016 | 2016-01-12 |  | 3 | 3
32 | Define Business Requirements | 2016-01-12 | 2016-01-12 |  | 4 | 6
33 | Define Environment System | 2016-02-12 | 2016-03-12 |  | 4 | 3
34 | Team Meeting | 28/11/2016 | 28/11/2016 | TaiNguyen |  | 3
35 | Review Business Workflow "Manage Banners" function | 28/11/2016 | 28/11/2016 |  | 3 | 3
36 | Review Business Workflow "Manage Homepage" function | 29/11/2016 | 29/11/2016 |  | 3 | 5
37 | Review Business Workflow "Manage Categories " function | 29/11/2016 | 29/11/2016 |  | 3 | 4
38 | Training Technical | 29/11/2016 | 29/11/2016 |  | 2 | 2
39 | Update Business workflow "Manage Banners" function | 30/11/2016 | 2016-01-12 |  | 3 | 4
40 | Update Business workflow "Manage Pop-ups" function | 30/11/2016 | 2016-01-12 |  | 3 | 2
41 | Define Current System | 2016-01-12 | 2016-01-12 |  | 2 | 1
42 | Define Context Diagram | 2016-02-12 | 2016-03-12 |  | 3 | 5
43 | Develop prototype for website | 2016-02-12 | 2016-03-12 |  | 6 | 9
44 | Team Meeting | 28/11/2016 | 28/11/2016 | XuanThaiHien |  | 3
45 | Review Business Workflow "Manage Banners" function | 28/11/2016 | 28/11/2016 |  | 2 | 3
46 | Review Business Workflow "Manage Pop-ups" function | 29/11/2016 | 29/11/2016 |  | 2 | 2
47 | Review Business Workflow "Manage Examination " function | 29/11/2016 | 29/11/2016 |  | 2 | 3
48 | Training Technical | 29/11/2016 | 29/11/2016 |  | 2 | 2
49 | Update Business workflow "Manage Examination " function | 30/11/2016 | 2016-01-12 |  | 2 | 3
50 | Define Business Context | 2016-01-12 | 2016-01-12 |  | 2 | 3
[5 empty] | ESTIMATE | ACTUAL
|  | Total |  | HaiTran | 25 | 34
|  |  |  | HienNguyen | 23 | 30
|  |  |  | KhoiNguyen | 19 | 28
|  |  |  | MinhDoan | 23 | 26
|  |  |  | TaiNguyen | 28 | 38
|  |  |  | XuanThaiHien | 12 | 19

## HaiTran
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## HienNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## KhoiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## TaiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## MinhDoan
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## XuanThaiHien
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time