## Dash Board
Current Task Status / Priority | High | Medium | Low | Total | % Of Total
New | 0 | 0 | 0 | 0 | 0%
Planned | 2 | 4 | 1 | 7 | 29.17%
In Progress | 4 | 0 | 1 | 5 | 20.83%
Closed | 1 | 4 | 0 | 5 | 20.83%
Reject | 2 | 3 | 2 | 7 | 29.17%
Total | 9 | 11 | 4 | 24 | 100%
% of Total | 37.5% | 45.83% | 16.67% | 100%
Risk department summary |  |  | Issue Status
Planning | 1 |  | Active | 5
Management | 8 |  | Fixed | 5
Requirement | 10
Architect | 2
Desgin | 2
Code | 1
Test | 0
Total | 24

## Risk List
ID | Risk Description | Department | Actual Status | Indentified_Date | Owner | Impact | Probability(scale) | Risk score | Priority | Action
1 | Estimates are inaccurate | Planning | In Progress | 2016-10-10 | HaiTran | 5 | 4 | 20 | High | Team meeting and re-estimate.
2 | Lack of needed knowledge | Code | In Progress | 2016-10-10 | MinhDoan | 5 | 4 | 20 | High | Reserch and increase effort to study new programming language.
3 | Errors in key project management processes | Management | Closed | 2016-10-10 | TaiNguyen | 4 | 3 | 12 | Medium | Team meeting to review each key process and modify them.
4 | Change management overload | Management | Planned | 2016-10-10 | MinhDoan | 3 | 3 | 9 | Medium | List changes, prioritize them and deal with customer
5 | Resource shortfalls | Management | Reject | 2016-10-10 | HienNguyen | 3 | 2 | 6 | Medium
6 | Learning curves lead to delays and cost overrun | Management | Reject | 2016-10-10 | HaiTran | 4 | 4 | 16 | High
7 | Resources are inexperienced | Management | Closed | 2016-10-10 | KhoiNguyen | 3 | 4 | 12 | Medium | All member research and read documents of previous course.
8 | Team members with negative attitudes towards the project | Management | Closed | 2016-10-10 | TaiNguyen | 2 | 4 | 8 | Medium | Team meeting to solve the problem.
9 | Scope is ill defined | Requirement | Planned | 2016-11-07 | HienNguyen | 5 | 2 | 10 | Medium | Team meeting to redefine scope and review with customer.
10 | Stakeholder conflict over proposed changes | Requirement | Planned | 2016-11-07 | HienNguyen | 3 | 1 | 3 | Low | Analyse clearly and review with stakeholeder.
11 | Inaccurate function priorities | Requirement | Closed | 2016-11-07 | MinhDoan | 5 | 3 | 15 | High | Review with customer to define clearly for function priorities.
12 | Change request conflicts with requirements | Requirement | Planned | 2016-11-07 | MinhDoan | 4 | 3 | 12 | Medium | Analyse impact of change to requirement and review with customer
13 | Customer rejects the prototype | Requirement | In Progress | 2016-11-07 | HaiTran | 4 | 4 | 16 | High | Request some prototypes of others website to customer, re-design follow the choice of customer.
14 | Stakeholder conflict | Requirement | Reject | 2016-11-07 | HienNguyen | 3 | 1 | 3 | Low
15 | Project team misunderstand requirements | Requirement | Reject | 2016-11-07 | KhoiNguyen | 5 | 4 | 20 | High
16 | Requirements are ambiguous | Requirement | Planned | 2016-11-07 | TaiNguyen | 5 | 5 | 25 | High | Customer meeting to review and make clear that requirement.
17 | Requirements are incomplete | Requirement | Reject | 2016-11-07 | TaiNguyen | 3 | 2 | 6 | Medium
18 | Customer has inaccurate expectations | Requirement | Planned | 2016-11-07 | MinhDoan | 5 | 3 | 15 | High | Propose to customer for he can understand his expectations.
19 | Delays to training impact the project | Management | In Progress | 2016-12-12 | TaiNguyen | 3 | 5 | 15 | High | Increase effort for all members.
20 | Architecture is infeasible | Architect | In Progress | 2016-12-12 | HaiTran | 1 | 2 | 2 | Low | Research and collect advices from professor
21 | Architecture is not fit for purpose | Architect | Reject | 2016-12-12 | KhoiNguyen | 4 | 2 | 8 | Medium
22 | Design lacks flexibility | Design | Reject | 2017-01-02 | HienNguyen | 4 | 1 | 4 | Low
23 | Design is not fit for purpose | Design | Planned | 2017-01-02 | KhoiNguyen | 4 | 2 | 8 | Medium | Research and re-design to fit the purpose.
24 | Resource is turn over | Management | Closed | 2017-02-02 | MinhDoan | 4 | 3 | 12 | Medium | Increase effort for all members.
25
26
27

## Issue List
ID | Issue Description | Department | Actual Status | Open_Date | Close_Date | Priority | Comment
1 | Estimates are inaccurate | Planning | Active | 24/10/2016 |  | High
2 | Lack of needed knowledge | Code | Active | 24/10/2016 |  | High | Lack of knowledge about coding and architecture.
3 | Resources are inexperienced | Management | Fixed | 24/10/2016 | 31/10/2016 | Medium
4 | Errors in key project management processes | Management | Fixed | 20/11/2016 | 28/11/2016 | Medium | Team meeting to define legend and fix process.
5 | Team members with negative attitudes towards the project | Management | Fixed | 29/11/2016 | 2016-05-12 | Medium
6 | Inaccurate function priorities | Management | Fixed | 2016-03-12 | 2016-07-12 | High | Need to meet customer and define clearly.
7 | Architecture is infeasible | Requirement | Active | 2017-04-01 |  | Low
8 | Delays to training impact the project | Management | Active | 23/1/2017 |  | High
9 | Customer rejects the prototype | Architect | Active | 23/2/2017 |  | High
10 | Resources is turn over | Management | Fixed | 23/2/2017 | 2017-01-03 | Medium
11
12
13

## Sheet1 (hidden)
Department
Planning
Requirement
Architect
Design
Code
Test
Management